## BPI and Key Tasks
BPI # | BPI Name | Step Owner | Implementation Steps | Estimated Implementation Timeline | Estimated Complexity | Key BPI Text | People, Process, Platform Changes People - Resource requests / capacity assessments Process - Key policy and process changes Platform - Technology Needs
1 | Consolidate resident-specific documentation asks at HHA submission | DHS | (DHS) Submit identified client-specific documentation to HPD at time of HHA submission. | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. These documents are: - Items collected for pre-screening, CityFHEPS, or Cash Assistance, such as: photo ID, social security card or WMS screenshot or individual tax ID number (ITIN), birth certificate for minors, and proof of legal guardianship of minors (if applicable). Many of these documents are collected to enter shelter and should be added by DHS to the HHA submission, rather than requesting again from the shelter resident. - Items created or collected by HRA and DHS as part of the CityFHEPS application in CurRENT or HOME (if available): "Shopping Letter" (DSS-7), "Household Share Letter" (DSS-7a), Tenant Contact Information (DSS-8b), and Request for Emergency Assistance (W-137A). Where documents are not fully completed until later (ex. W-137A), DHS can pass over a partially completed version of the form so as to streamline the landlord completion of the form later in the process. - Documentation needed if selecting a reasonable accommodation need in HHA: Certification of Eligibility for Disability Unit (Attachment I-2). Currently, this document is not provided until the eligibility appointment or during the pending documents step. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | DHS | (HPD) Reject HHAs that do not include all resident-specific documentation. | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | HPD | (HPD) Inform marketing agents of updated documentation policy and that WMS print-out of SSN information is sufficient to meet referral needs and compliance requirements | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | DHS | (DHS) Share the Social Security Number (SSN) validation screen with HPD at time of HHA submission. Specifically, capture validated SSN from WMS screen and submit with HHA. | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | DHS | (DHS/shelter providers) Inform providers of documentation needed for HHA submission. | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | HPD | (HPD) Provide a checklist of any additional documents that may be requested later in the process if the shelter resident is matched with a LIHTC unit (e.g., tax returns, income, and asset documentation, etc.). | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | HRA | (HRA) Provide a checklist of any additional documents that may be requested later in the process for the CityFHEPS application (e.g., proof of income from the last 30 days, etc.) | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
1 | Consolidate resident-specific documentation asks at HHA submission | HPD/HRA | (HPD/HRA) Continue to revisit documentation requests based on changing policies. For example, if the pre-screening process is removed, SSN validation may no longer be needed from the shelter resident at HHA submission. | Short-term | Low | Collecting documentation requires extensive coordination with clients, providers, marketing agents and DHS and HPD teams. Much of these documents are client-specific and potentially already known to DHS and HRA teams. DHS should collect and distribute this documentation to HPD at the beginning of this process, specifically at HHA submission, to reduce back-and-forth during lease-up. This will reduce the number of "isolated" asks for shelter resident-specific documentation during lease-up. | Process
2 | Create a universal Release of Information (ROI) consent form and complete with HHA submission | HPD | (HPD) Review the existing ROI forms from marketing agents and sponsors/landlords and confirm any language and notices required by law. Draft universal ROI based on these data elements and decision. | Short-term | Low | Create a universal, standardized Release of Information (ROI) consent form that contains all the required data elements and legal notices needed for HPD HPS to make a client referral to the marketing agent and initiate the pre-screening. The universal, standardized ROI would also be completed as part of the submission of the HHA. | Process
2 | Create a universal Release of Information (ROI) consent form and complete with HHA submission | DHS | (DHS) Digitize the universal ROI form to expedite the signing of the form by shelter residents and ease of transmission between shelter providers, HPS, and marketing agents. Enable completion of ROI by shelter residents with shelter provider assistance in DHS’ HOME system | Short-term | Low | Create a universal, standardized Release of Information (ROI) consent form that contains all the required data elements and legal notices needed for HPD HPS to make a client referral to the marketing agent and initiate the pre-screening. The universal, standardized ROI would also be completed as part of the submission of the HHA. | Platform
2 | Create a universal Release of Information (ROI) consent form and complete with HHA submission | HPD | (HPD) Roll out the universal ROI form to all marketing agents with timeline of the expected transition to the new form. Update the relevant material and policies (e.g., HPD Marketing Handbook). | Short-term | Low | Create a universal, standardized Release of Information (ROI) consent form that contains all the required data elements and legal notices needed for HPD HPS to make a client referral to the marketing agent and initiate the pre-screening. The universal, standardized ROI would also be completed as part of the submission of the HHA. | Process
2 | Create a universal Release of Information (ROI) consent form and complete with HHA submission | DHS | (DHS) Include the universal ROI as part of the HHA submission. | Short-term | Low | Create a universal, standardized Release of Information (ROI) consent form that contains all the required data elements and legal notices needed for HPD HPS to make a client referral to the marketing agent and initiate the pre-screening. The universal, standardized ROI would also be completed as part of the submission of the HHA. | Process
3 | Remove third-party reviews as dependency for lease-up | HPD/HDC | (HDC/HPD) Notify marketing agents that HDC will no longer complete full income or modified file reviews for homeless set-aside units. | Short-term | Low | Establish a policy that any third-party review conducted for a homeless set-aside unit, cannot be a dependency to lease-up. Any third-party reviews completed should occur in parallel to lease-up processes where needed. | Process
3 | Remove third-party reviews as dependency for lease-up | HPD | (HPD) Communicate to marketing agents that if they proceed with third-party file reviews, they cannot be a dependency for lease signing | Short-term | Low | Establish a policy that any third-party review conducted for a homeless set-aside unit, cannot be a dependency to lease-up. Any third-party reviews completed should occur in parallel to lease-up processes where needed. | Process
3 | Remove third-party reviews as dependency for lease-up | HPD | (HPD) Update the HPD Marketing Handbook to reflect updated policy. | Short-term | Low | Establish a policy that any third-party review conducted for a homeless set-aside unit, cannot be a dependency to lease-up. Any third-party reviews completed should occur in parallel to lease-up processes where needed. | Process
4 | Update HPD policies to remove credit and criminal background checks during the pre-screening process |  | (HPD) Continue to work towards removing the credit check that is currently executed by marketing agents for shelter residents. | Medium-term | Medium | Eliminate the entire pre-screening process step by discontinuing credit and criminal background checks from the homeless set-aside placement process. As this step is the third longest source of delays according to OMB Policy and Operations Research Task Force analysis, removing it would accelerate the lease-up process. The shelter resident would be able to proceed from shelter resident/unit match to either: (1) Complete landlord paper (if non-LIHTC unit) or (2) straight to provide LIHTC documentation (if LIHTC unit). (Note - credit check removal effort underway). | Process
4 | Update HPD policies to remove credit and criminal background checks during the pre-screening process | HPD | (HPD) Make decision on removal of the criminal credit and criminal background check of the shelter residents as part of the pre-screening process for homeless set-aside placement applicants. | Medium-term | Medium | Eliminate the entire pre-screening process step by discontinuing credit and criminal background checks from the homeless set-aside placement process. As this step is the third longest source of delays according to OMB Policy and Operations Research Task Force analysis, removing it would accelerate the lease-up process. The shelter resident would be able to proceed from shelter resident/unit match to either: (1) Complete landlord paper (if non-LIHTC unit) or (2) straight to provide LIHTC documentation (if LIHTC unit). (Note - credit check removal effort underway). | Process
4 | Update HPD policies to remove credit and criminal background checks during the pre-screening process | HPD | (HPD) Update program policy and the HPD Marketing Handbook to remove credit and criminal background checks. | Medium-term | Medium | Eliminate the entire pre-screening process step by discontinuing credit and criminal background checks from the homeless set-aside placement process. As this step is the third longest source of delays according to OMB Policy and Operations Research Task Force analysis, removing it would accelerate the lease-up process. The shelter resident would be able to proceed from shelter resident/unit match to either: (1) Complete landlord paper (if non-LIHTC unit) or (2) straight to provide LIHTC documentation (if LIHTC unit). (Note - credit check removal effort underway). | Process
4 | Update HPD policies to remove credit and criminal background checks during the pre-screening process | DHS | (DHS) Update Universal ROI to remove any pre-screening references. | Medium-term | Medium | Eliminate the entire pre-screening process step by discontinuing credit and criminal background checks from the homeless set-aside placement process. As this step is the third longest source of delays according to OMB Policy and Operations Research Task Force analysis, removing it would accelerate the lease-up process. The shelter resident would be able to proceed from shelter resident/unit match to either: (1) Complete landlord paper (if non-LIHTC unit) or (2) straight to provide LIHTC documentation (if LIHTC unit). (Note - credit check removal effort underway). | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | HPD | (HPD) Work with marketing agents to develop a LIHTC questionnaire to facilitate identifying shelter resident and LIHTC-specific documentation needed based upon resident characteristics (e.g., veteran, student, sources of income). The shelter resident would be asked a series of questions about the household and sources of income, and based on those responses, a list of documents would be generated for the resident to compile according to the 10-day timeline. Develop the interactive questionnaire using a web-form that would allow HPD to see the time stamp for completion and track the 10-day timeline | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | HPD | (HPD) Shelter resident should complete the questionnaire at the time the shelter resident is matched. Policies around return of question should allow for timeline extensions due to extenuating circumstances and reasonable accommodations on a case-by-case basis. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | HPD | (HPD) Implement the questionnaire and send to DHS along with the match information once it is identified that the resident has been matched with a LIHTC unit. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | DHS | (DHS) Train shelter providers on documentation needs for LIHTC units and completing the questionnaire with the shelter resident once matched to a LIHTC unit. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | HPD | (HPD) Remove the eligibility appointment and associated scheduling from the homeless set-aside placement process for LIHTC. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | Marketing Agent | (Marketing agents) Marketing agents to assess LIHTC eligibility based on documentation. If questions arise on documentation, they are to call the shelter resident directly. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
5 | Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process | HPD | (HPD) Notify HPS staff, shelter providers, DHS, and marketing agents of process updates. | Medium-term | Medium | Reduce the lease-up timeframe for LIHTC units by removing the eligibility appointment. The shelter resident would still be supported in the compiling and provision of LIHTC documentation to the marketing agent by completing a LIHTC questionnaire with the shelter provider to identify their customized set of documents to produce. Additionally, given other BPIs pertaining to consolidating documentation on behalf of the client and higher standards on the quality of HHA submissions, the need for specific eligibility appointments should become redundant. The implementation of this BPI would also align the homeless set-aside placement process for LIHTC units with the process for LIHTC units available through HPD’s Housing Lottery program. | Process
6 | Establish a cloud-based document storage solution to reduce handoffs | HPD | (HPD) Identify cloud-based storage solution based upon HPD technical infrastructure and Office of Technology and Innovation requirements, if applicable. | Medium-term | Medium | Address the manual exchange of sensitive documentation over email, duplicative requests for information, and the many handoffs between parties to share information by establishing a cloud-based document storage solution. The solution would allow for documentation to be shared, viewed, and uploaded by HPS, DHS, HRA, and marketing agents. The solution would also provide improved access and security measures to better safeguard the sensitive documentation being shared. | Platform
6 | Establish a cloud-based document storage solution to reduce handoffs | HPD | (HPD) Define user roles and access privileges for the cloud-based solution (read only, who has access to shelter resident documentation, etc.). | Medium-term | Medium | Address the manual exchange of sensitive documentation over email, duplicative requests for information, and the many handoffs between parties to share information by establishing a cloud-based document storage solution. The solution would allow for documentation to be shared, viewed, and uploaded by HPS, DHS, HRA, and marketing agents. The solution would also provide improved access and security measures to better safeguard the sensitive documentation being shared. | Platform
6 | Establish a cloud-based document storage solution to reduce handoffs | HPD | (HPD) Work with Legal to develop a Memorandum of Understanding (MOU) or Data Use Agreement (DUA) for data-sharing across HPD, DHS, HRA, HDC, and marketing agents that meets privacy requirements. | Medium-term | Medium | Address the manual exchange of sensitive documentation over email, duplicative requests for information, and the many handoffs between parties to share information by establishing a cloud-based document storage solution. The solution would allow for documentation to be shared, viewed, and uploaded by HPS, DHS, HRA, and marketing agents. The solution would also provide improved access and security measures to better safeguard the sensitive documentation being shared. | Process
6 | Establish a cloud-based document storage solution to reduce handoffs | HPD | (HPD) Provision access for key end users including DHS, shelter providers, HRA, and marketing agents. | Medium-term | Medium | Address the manual exchange of sensitive documentation over email, duplicative requests for information, and the many handoffs between parties to share information by establishing a cloud-based document storage solution. The solution would allow for documentation to be shared, viewed, and uploaded by HPS, DHS, HRA, and marketing agents. The solution would also provide improved access and security measures to better safeguard the sensitive documentation being shared. | Platform
6 | Establish a cloud-based document storage solution to reduce handoffs | HPD | (DHS/HPD) Provide training to impacted process participants: shelter providers, marketing agents, HPS staff, DHS, HRA. | Medium-term | Medium | Address the manual exchange of sensitive documentation over email, duplicative requests for information, and the many handoffs between parties to share information by establishing a cloud-based document storage solution. The solution would allow for documentation to be shared, viewed, and uploaded by HPS, DHS, HRA, and marketing agents. The solution would also provide improved access and security measures to better safeguard the sensitive documentation being shared. | Process
7 | Create a golden record for property owners and units ahead of submission processes | HPD | (DHS/HPD) Assess level of effort for adding new landlords into CurRENT, including for the creation of a new user role for HPD and DHS CAR. Based upon resourcing capacity, make determination on who should take on this responsibility. | Medium-term | Medium | Establish a “landlord golden record” that is accessible by all agencies involved in the homeless set-aside placement process. The creation of a golden record earlier in the process would reduce downstream process delays associated with reconciling landlord information that is currently occurring between HRPU and the HRA Landlord Management Unit (LMU). Additionally, the creation of the landlord golden record in one single application would reduce duplicative work across HPD and HRA. | People
7 | Create a golden record for property owners and units ahead of submission processes | HRA | (HRA) Grant business unit responsible for creating golden record access to add landlords into CurRENT and to submit help desk assistance for CurRENT technical issues. | Medium-term | Medium | Establish a “landlord golden record” that is accessible by all agencies involved in the homeless set-aside placement process. The creation of a golden record earlier in the process would reduce downstream process delays associated with reconciling landlord information that is currently occurring between HRPU and the HRA Landlord Management Unit (LMU). Additionally, the creation of the landlord golden record in one single application would reduce duplicative work across HPD and HRA. | Platform
7 | Create a golden record for property owners and units ahead of submission processes | HPD | (HPD) Export landlord information from CurRENT and compare to open units for HPD landlords providing set-aside units using common identifier “Landlord TIN.” Identify landlords that are not yet entered. | Medium-term | Medium | Establish a “landlord golden record” that is accessible by all agencies involved in the homeless set-aside placement process. The creation of a golden record earlier in the process would reduce downstream process delays associated with reconciling landlord information that is currently occurring between HRPU and the HRA Landlord Management Unit (LMU). Additionally, the creation of the landlord golden record in one single application would reduce duplicative work across HPD and HRA. | Platform
7 | Create a golden record for property owners and units ahead of submission processes | HRA | (HRA) Provide cross-training to HPD on CurRENT and how to add and process landlord changes. Training also to be provided on common errors in the landlord record. | Medium-term | Medium | Establish a “landlord golden record” that is accessible by all agencies involved in the homeless set-aside placement process. The creation of a golden record earlier in the process would reduce downstream process delays associated with reconciling landlord information that is currently occurring between HRPU and the HRA Landlord Management Unit (LMU). Additionally, the creation of the landlord golden record in one single application would reduce duplicative work across HPD and HRA. | Process
7 | Create a golden record for property owners and units ahead of submission processes | HPD | (HPD) Given future system scope for homeless set-aside placement process systems, identify requirement for landlord profile and record integration with HRA and DHS. | Medium-term | Medium | Establish a “landlord golden record” that is accessible by all agencies involved in the homeless set-aside placement process. The creation of a golden record earlier in the process would reduce downstream process delays associated with reconciling landlord information that is currently occurring between HRPU and the HRA Landlord Management Unit (LMU). Additionally, the creation of the landlord golden record in one single application would reduce duplicative work across HPD and HRA. | Platform
8 | Streamline the pre-screening process by setting a timeframe for marketing agents to complete | HPD | (HPD) Establish a timeline by which marketing agents are required to complete the pre-screening and return the results to HPD. Three (3) business days is recommended. | Short-term | Low | Reduce the time spent on the Awaiting Pre-screening Results step by defining a Service Level Agreement (SLA) of three days for marketing agents to complete the pre-screening and return the results to HPD. If the marketing agent fails to meet the SLA, HPS will not send additional referrals to the marketing agent until results are returned. | Process
8 | Streamline the pre-screening process by setting a timeframe for marketing agents to complete | HPD | (HPD) Document updated pre-screening policies with this SLA and include implications for non-compliance and repeated infractions | Short-term | Low | Reduce the time spent on the Awaiting Pre-screening Results step by defining a Service Level Agreement (SLA) of three days for marketing agents to complete the pre-screening and return the results to HPD. If the marketing agent fails to meet the SLA, HPS will not send additional referrals to the marketing agent until results are returned. | Process
8 | Streamline the pre-screening process by setting a timeframe for marketing agents to complete | HPD | (HPD) Communicate the updated pre-screening policy to HPS personnel and marketing agents. | Short-term | Low | Reduce the time spent on the Awaiting Pre-screening Results step by defining a Service Level Agreement (SLA) of three days for marketing agents to complete the pre-screening and return the results to HPD. If the marketing agent fails to meet the SLA, HPS will not send additional referrals to the marketing agent until results are returned. | Process
8 | Streamline the pre-screening process by setting a timeframe for marketing agents to complete | HPD | (HPD) Use the MS Access Database to track marketing agent performance of compliance with pre-screening policy. Analyze the performance monthly and discuss performance with marketing agents as part of quarterly or semi-annual marketing agent engagement sessions (See BPI 31: Improve marketing agent engagement through quarterly or semi-annual meetings) | Short-term | Low | Reduce the time spent on the Awaiting Pre-screening Results step by defining a Service Level Agreement (SLA) of three days for marketing agents to complete the pre-screening and return the results to HPD. If the marketing agent fails to meet the SLA, HPS will not send additional referrals to the marketing agent until results are returned. | Platform
9 | Document and enforce a LIHTC document submission timeline for shelter residents | HPD | (HPD) Update program policies with a timeframe for shelter residents to submit LIHTC documentation. The policy should include a reasonable accommodation process. If reasonable accommodations are not applicable and the timeframe is not met, the resident's HHA will be removed from HPD's queue of applicants. The shelter resident may resubmit their HHA and restart the process. When a resident is removed from the queue, notify HRPU and shelter providers. | Short-term | Low | Reduce the lease-up timeframe for LIHTC units by establishing a set time for shelter residents to provide documentation to the marketing agent when matched to a LIHTC unit. In the current homeless set-aside placement process, while there is a timeframe and deadline provided for shelter residents to supply LIHTC documentation within ten days, it is not consistently enforced. Reasonable accommodations scenarios are also not documented. Currently, the Pending Documents stage lasts, on average, 30 days and compared to a target of 10 days. Applying a deadline for the provision of LIHTC documents by shelter residents will address the current delays associated with this process step and lease-up of units. | Process
9 | Document and enforce a LIHTC document submission timeline for shelter residents | HPD | (HPD) Notify HPS staff, shelter providers, DHS, and marketing agents of process updates. | Short-term | Low | Reduce the lease-up timeframe for LIHTC units by establishing a set time for shelter residents to provide documentation to the marketing agent when matched to a LIHTC unit. In the current homeless set-aside placement process, while there is a timeframe and deadline provided for shelter residents to supply LIHTC documentation within ten days, it is not consistently enforced. Reasonable accommodations scenarios are also not documented. Currently, the Pending Documents stage lasts, on average, 30 days and compared to a target of 10 days. Applying a deadline for the provision of LIHTC documents by shelter residents will address the current delays associated with this process step and lease-up of units. | Process
9 | Document and enforce a LIHTC document submission timeline for shelter residents | DHS | (DHS) Train shelter providers on policy updates and supporting shelter residents in obtaining LIHTC documentation. | Short-term | Low | Reduce the lease-up timeframe for LIHTC units by establishing a set time for shelter residents to provide documentation to the marketing agent when matched to a LIHTC unit. In the current homeless set-aside placement process, while there is a timeframe and deadline provided for shelter residents to supply LIHTC documentation within ten days, it is not consistently enforced. Reasonable accommodations scenarios are also not documented. Currently, the Pending Documents stage lasts, on average, 30 days and compared to a target of 10 days. Applying a deadline for the provision of LIHTC documents by shelter residents will address the current delays associated with this process step and lease-up of units. | Process
9 | Document and enforce a LIHTC document submission timeline for shelter residents | DHS | (DHS) (Also mentioned in BPI 32) Develop shelter resident homeless set-aside placement process toolkit, communicate documentation timelines and expectations to shelter residents at the beginning when their HHA is submitted. | Short-term | Low | Reduce the lease-up timeframe for LIHTC units by establishing a set time for shelter residents to provide documentation to the marketing agent when matched to a LIHTC unit. In the current homeless set-aside placement process, while there is a timeframe and deadline provided for shelter residents to supply LIHTC documentation within ten days, it is not consistently enforced. Reasonable accommodations scenarios are also not documented. Currently, the Pending Documents stage lasts, on average, 30 days and compared to a target of 10 days. Applying a deadline for the provision of LIHTC documents by shelter residents will address the current delays associated with this process step and lease-up of units. | Process
9 | Document and enforce a LIHTC document submission timeline for shelter residents | HPD | (HPD) Use current MS Access Database to track shelter resident compliance with LIHTC documentation submission policy. Analyze the performance monthly to assess for areas of improvement. Share with DHS for performance management of shelter providers assisting shelter residents with obtaining documentation. | Short-term | Low | Reduce the lease-up timeframe for LIHTC units by establishing a set time for shelter residents to provide documentation to the marketing agent when matched to a LIHTC unit. In the current homeless set-aside placement process, while there is a timeframe and deadline provided for shelter residents to supply LIHTC documentation within ten days, it is not consistently enforced. Reasonable accommodations scenarios are also not documented. Currently, the Pending Documents stage lasts, on average, 30 days and compared to a target of 10 days. Applying a deadline for the provision of LIHTC documents by shelter residents will address the current delays associated with this process step and lease-up of units. | Platform
10 | Implement a policy to limit number of units a shelter residents can reject | HPD | (HPD) Update homeless set-aside policies to reflect a maximum of two referrals per HHA. If shelter resident rejects two referrals, HPD would remove the resident’s HHA from the pool of applicants and notify DHS that the resident’s HHA was removed. The resident would then have the option to reapply and resubmit an HHA. | Medium-term | Low | Reduce duplicative work associated with multiple shelter resident/unit matches by implementing a policy that, for each HHA submission, shelter residents will only be able to reject a certain number of units before being removed from the pool of applicants with the option to reapply. The recommended number of maximum rejections is two with reasonable accommodations provided. Additionally, the policy should consider that residents should not be penalized for matches that do not meet their required criteria as stated on the HHA (e.g., a resident with documented mobility needs is matched to an inaccessible unit). Note: As this BPI would enforce stricter perimeters on the shelter resident to accepting the referral, HPD should in parallel consider efforts to improve the matching process. Long-term improvements in this area are identified in BPI #19. | Process
10 | Implement a policy to limit number of units a shelter residents can reject | HPD | (HPD) Work with DHS to determine reasonable exceptions to this policy to allow for extenuating circumstances and document in the policy. | Medium-term | Low | Reduce duplicative work associated with multiple shelter resident/unit matches by implementing a policy that, for each HHA submission, shelter residents will only be able to reject a certain number of units before being removed from the pool of applicants with the option to reapply. The recommended number of maximum rejections is two with reasonable accommodations provided. Additionally, the policy should consider that residents should not be penalized for matches that do not meet their required criteria as stated on the HHA (e.g., a resident with documented mobility needs is matched to an inaccessible unit). Note: As this BPI would enforce stricter perimeters on the shelter resident to accepting the referral, HPD should in parallel consider efforts to improve the matching process. Long-term improvements in this area are identified in BPI #19. | Process
10 | Implement a policy to limit number of units a shelter residents can reject | HPD | (DHS) Provide training for shelter providers to convey these expectations to shelter residents. | Medium-term | Low | Reduce duplicative work associated with multiple shelter resident/unit matches by implementing a policy that, for each HHA submission, shelter residents will only be able to reject a certain number of units before being removed from the pool of applicants with the option to reapply. The recommended number of maximum rejections is two with reasonable accommodations provided. Additionally, the policy should consider that residents should not be penalized for matches that do not meet their required criteria as stated on the HHA (e.g., a resident with documented mobility needs is matched to an inaccessible unit). Note: As this BPI would enforce stricter perimeters on the shelter resident to accepting the referral, HPD should in parallel consider efforts to improve the matching process. Long-term improvements in this area are identified in BPI #19. | Process
10 | Implement a policy to limit number of units a shelter residents can reject | HPD | (DHS) Develop written material for shelter resident conveying policy in plain language, easy to understand format. (See BPI 32: Develop shelter resident homeless set-aside placement process toolkit for how this can be communicated to the shelter resident at the beginning of the process). | Medium-term | Low | Reduce duplicative work associated with multiple shelter resident/unit matches by implementing a policy that, for each HHA submission, shelter residents will only be able to reject a certain number of units before being removed from the pool of applicants with the option to reapply. The recommended number of maximum rejections is two with reasonable accommodations provided. Additionally, the policy should consider that residents should not be penalized for matches that do not meet their required criteria as stated on the HHA (e.g., a resident with documented mobility needs is matched to an inaccessible unit). Note: As this BPI would enforce stricter perimeters on the shelter resident to accepting the referral, HPD should in parallel consider efforts to improve the matching process. Long-term improvements in this area are identified in BPI #19. | Process
11 | Provide clear and consistent unit information to shelter residents at the time of resident/unit match | HPD | (HPD) Work with marketing agents to develop marketing materials (e.g., photos, video, etc.) for homeless set-aside units, using what is provided for Housing Lottery units as a guide. | Medium-term | Low | Provide the shelter resident more information related to the prospective match to reduce the likelihood that a shelter resident declines a unit later in the process, as well as to better mark for reasons that could have been known earlier. When mismatches occur in the homeless set-aside placement process steps must be duplicated and lease-up times are elongated for units. | Process
11 | Provide clear and consistent unit information to shelter residents at the time of resident/unit match | HPD | (HPD) Develop template for marketing agents to use to provide unit marketing information to HPD. | Medium-term | Low | Provide the shelter resident more information related to the prospective match to reduce the likelihood that a shelter resident declines a unit later in the process, as well as to better mark for reasons that could have been known earlier. When mismatches occur in the homeless set-aside placement process steps must be duplicated and lease-up times are elongated for units. | Process
11 | Provide clear and consistent unit information to shelter residents at the time of resident/unit match | HPD | (HPD) Update Marketing Handbook with marketing guidelines for homeless set-aside units and incorporate into quarterly marketing agent meetings. | Medium-term | Low | Provide the shelter resident more information related to the prospective match to reduce the likelihood that a shelter resident declines a unit later in the process, as well as to better mark for reasons that could have been known earlier. When mismatches occur in the homeless set-aside placement process steps must be duplicated and lease-up times are elongated for units. | Process
11 | Provide clear and consistent unit information to shelter residents at the time of resident/unit match | DHS | (DHS) Provide training for shelter providers to reinforce providing all unit information to the shelter resident at the time of match. | Medium-term | Low | Provide the shelter resident more information related to the prospective match to reduce the likelihood that a shelter resident declines a unit later in the process, as well as to better mark for reasons that could have been known earlier. When mismatches occur in the homeless set-aside placement process steps must be duplicated and lease-up times are elongated for units. | Process
11 | Provide clear and consistent unit information to shelter residents at the time of resident/unit match | DHS | (HPD) Identify key performance indicators to measure the success of implementing this recommendation (such as reduction in shelter resident rejection of units late in the process, faster acceptance/denials, etc.). | Medium-term | Low | Provide the shelter resident more information related to the prospective match to reduce the likelihood that a shelter resident declines a unit later in the process, as well as to better mark for reasons that could have been known earlier. When mismatches occur in the homeless set-aside placement process steps must be duplicated and lease-up times are elongated for units. | Process
12 | Implement a process step and timeframe for obtaining resident acceptance/rejection of unit | HPD | (HPD) Implement process to collect shelter resident approve/reject of unit. Can create different options: use a web form, MS Forms, phone call or email confirmation. | Medium-term | Low | Create a clear process step to record the shelter resident acceptance or denial of a unit following the initial shelter resident/unit match. Within three days of being matched to a unit, HPS must collect a decision from the shelter resident and record it in the HPD Database. If the timeframe is not met, then the shelter resident moves to the end of the queue. Circumstances for reasonable accommodation for this policy should be established. | Platform
12 | Implement a process step and timeframe for obtaining resident acceptance/rejection of unit | HPD | (HPD) Update lease-up policies to be updated to reflect the following: - A decision to accept or reject the unit must be provided and recorded within 3 business days. If a decision is not provided in the required timeframe, the shelter resident’s application moves to the end of the pool of applicants. - Number of attempts to contact the resident should be included in the policy. | Medium-term | Low | Create a clear process step to record the shelter resident acceptance or denial of a unit following the initial shelter resident/unit match. Within three days of being matched to a unit, HPS must collect a decision from the shelter resident and record it in the HPD Database. If the timeframe is not met, then the shelter resident moves to the end of the queue. Circumstances for reasonable accommodation for this policy should be established. | Process
12 | Implement a process step and timeframe for obtaining resident acceptance/rejection of unit | DHS | (DHS) Provide training for shelter providers to convey these expectations to shelter residents and to timely convey shelter resident’s decision to HPD. | Medium-term | Low | Create a clear process step to record the shelter resident acceptance or denial of a unit following the initial shelter resident/unit match. Within three days of being matched to a unit, HPS must collect a decision from the shelter resident and record it in the HPD Database. If the timeframe is not met, then the shelter resident moves to the end of the queue. Circumstances for reasonable accommodation for this policy should be established. | Process
12 | Implement a process step and timeframe for obtaining resident acceptance/rejection of unit | DHS | (DHS) Develop written material for shelter resident conveying policy in plain language, easy to understand format. (See BPI 32: Develop shelter resident homeless set-aside placement process toolkit for how this can be communicated to the shelter resident at the beginning of the process). | Medium-term | Low | Create a clear process step to record the shelter resident acceptance or denial of a unit following the initial shelter resident/unit match. Within three days of being matched to a unit, HPS must collect a decision from the shelter resident and record it in the HPD Database. If the timeframe is not met, then the shelter resident moves to the end of the queue. Circumstances for reasonable accommodation for this policy should be established. | Process
13 | Publish a definitive guide for LIHTC audit standards | HPD/HDC | (HPD/HDC) HPD and HDC to conduct an internal review of the current standards used for findings of LIHTC non-compliance so that they do not exceed federal standards. | Long-term | Medium | Address delays in the “Pending Documents” and “Awaiting eligibility screening results” steps by reducing unnecessary or excessive numbers of documents requested by marketing agents of shelter residents for LIHTC unit eligibility determinations. This BPI involves providing marketing agents and syndicators with a single source of information they can reply upon for LIHTC compliance standards that does not exceed federal minimums. | Process
13 | Publish a definitive guide for LIHTC audit standards | HPD/HDC | (HPD/HDC) Publish a definitive guide on LIHTC compliance expectations for marketing agents and syndicators. | Long-term | Medium | Address delays in the “Pending Documents” and “Awaiting eligibility screening results” steps by reducing unnecessary or excessive numbers of documents requested by marketing agents of shelter residents for LIHTC unit eligibility determinations. This BPI involves providing marketing agents and syndicators with a single source of information they can reply upon for LIHTC compliance standards that does not exceed federal minimums. | Process
13 | Publish a definitive guide for LIHTC audit standards | HPD/HDC | (HPD/HDC) Engage marketing agents and syndicators about the City-approved guidance. | Long-term | Medium | Address delays in the “Pending Documents” and “Awaiting eligibility screening results” steps by reducing unnecessary or excessive numbers of documents requested by marketing agents of shelter residents for LIHTC unit eligibility determinations. This BPI involves providing marketing agents and syndicators with a single source of information they can reply upon for LIHTC compliance standards that does not exceed federal minimums. | Process
14 | Conduct periodic internal desk reviews of homeless set-aside placement cases and lease-ups | HPD | (HPD) Determine approach, process, and procedures for internal desk review of referrals and lease-up process with clear objectives and goals for continuous process evaluation and improvement. | Long-term | Medium | Implement regular HPS program monitoring to identify areas of continuous process improvement and where practice may not align to policy, indicating a need to revisit policies and procedures. This BPI recommends that HPD conduct periodic desk reviews of homeless set-aside placement cases (referrals and lease-up process) with focus on the factors impacting lease-up timeframes (e.g., unit types, household size). The desk review will allow HPD to review case notes, data, data sources and conduct interviews, as necessary, to understand the journey of the units and the households in the process. | Process
14 | Conduct periodic internal desk reviews of homeless set-aside placement cases and lease-ups | HPD | (HPD) Implement desk review procedures, including cadence of review, access to case files/notes and data, and any other needed qualitative and quantitative information (e.g., interviews). | Long-term | Medium | Implement regular HPS program monitoring to identify areas of continuous process improvement and where practice may not align to policy, indicating a need to revisit policies and procedures. This BPI recommends that HPD conduct periodic desk reviews of homeless set-aside placement cases (referrals and lease-up process) with focus on the factors impacting lease-up timeframes (e.g., unit types, household size). The desk review will allow HPD to review case notes, data, data sources and conduct interviews, as necessary, to understand the journey of the units and the households in the process. | Process
14 | Conduct periodic internal desk reviews of homeless set-aside placement cases and lease-ups | HPD | (HPD) Report out on lessons learned for performance management, personnel training, marketing agent engagement, inter-agency engagement, and more. | Long-term | Medium | Implement regular HPS program monitoring to identify areas of continuous process improvement and where practice may not align to policy, indicating a need to revisit policies and procedures. This BPI recommends that HPD conduct periodic desk reviews of homeless set-aside placement cases (referrals and lease-up process) with focus on the factors impacting lease-up timeframes (e.g., unit types, household size). The desk review will allow HPD to review case notes, data, data sources and conduct interviews, as necessary, to understand the journey of the units and the households in the process. | Process
14 | Conduct periodic internal desk reviews of homeless set-aside placement cases and lease-ups | (HPD/DHS/HRA) | (HPD/DHS/HRA) Incorporate desk review findings into the homeless set-aside process through changes to policy, procedures, training, and/or dashboard metrics and monitoring (BPI 20). | Long-term | Medium | Implement regular HPS program monitoring to identify areas of continuous process improvement and where practice may not align to policy, indicating a need to revisit policies and procedures. This BPI recommends that HPD conduct periodic desk reviews of homeless set-aside placement cases (referrals and lease-up process) with focus on the factors impacting lease-up timeframes (e.g., unit types, household size). The desk review will allow HPD to review case notes, data, data sources and conduct interviews, as necessary, to understand the journey of the units and the households in the process. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Identify areas of marketing agent performance that require ongoing monitoring and improvement to speed up the homeless set-aside lease-up process. | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Develop key performance indicators (KPIs) and SLAs that address the identified areas of needed monitoring and improvement | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Communicate new performance standards to the marketing agents. Update the HPD Marketing Handbook to reflect performance standards. | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Develop training material for marketing agents to support their ongoing performance development and adherence to SLAs. | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Incorporate findings into the homeless set-aside process through changes to policy, procedures, training, and/or dashboard metrics and monitoring (BPI 20). | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
15 | Implement performance standards to remove marketing agents from the HPD pre-qualified list | HPD | (HPD) Reassess and update marketing agent performance management standards at a regular cadence. | Long-term | Medium | Implement standards that HPD can utilize to monitor and assess marketing agent performance. According to OMB Policy and Operations Research Task Force data analysis, homeless set-aside unit fill rates vary substantially by marketing agent, even when accounting for differences in unit characteristics (e.g., size, borough, time of year, new construction, or re-rental, LIHTC or non-LIHTC, etc.). There are several marketing agents that under-perform or over-perform based on their unit characteristics. Areas of needed performance measurements for marketing agents can include adherence to policies, level of communication with HPD and DHS, adherence to SLAs and timeframes, and more. | Process
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | HPD | (HPD) HPS to work with the HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Process
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | DHS | (DHS) Assess system capabilities for updates and integration, including the resources needed to update the HHA questionnaire in HOME and the integration requirements between HOME and identified HRA systems (see BPI 17 and 18 for integration expectations for the HHA). | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Platform
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | HPD | (HPD) Identify criteria needed to add to the HHA to improve downstream matching. | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Process
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | DHS | (DHS) Implement updates into HOME and paper based HHAs. | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Platform
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | DHS/HPD | (DHS/HPD) Perform user testing of updated HHA in HOME and for HPD database import. | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Platform
16 | Implement changes to information requested on the Homeless Housing Application (HHA) to improve downstream matching | DHS | (DHS) Develop training for shelter providers on the additional data elements and facilitating conversations with shelter residents to complete the new data elements. Talking points can be provided to explain how shelter resident preferences in the HHA may impact their referral options and how likely they will be matched with housing. | Medium-term | Medium | Improve the accuracy of the shelter resident to unit match and reduce the rework associated with unsuccessful matches. HPS should work HPD Center for Research on Housing Opportunity, Mobility, and Equity to develop questions to facilitate residents sharing geographical preferences that will help them get housed successfully and meet their long-term goals (e.g., location of employment, locations of key medical and social services, etc.). Note: In the long-term, the HHA should be considered in the future state HPD system, noted in BPI #19. | Process
17 | Improve validation of HHAs in the HPD referral pool | DHS/HRA | (DHS/HRA) Work with technology staff to identify an automated approach to comparing the existing HHA pool with the above data sources. Conduct IT assessment of systems’ current state and future state requirements. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Platform
17 | Improve validation of HHAs in the HPD referral pool | DHS/HRA | (DHS/HRA) Run daily validations of HHAs submitted against recommended data sources. Generate a daily file of updates and share with HPD. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Platform
17 | Improve validation of HHAs in the HPD referral pool | HPD | Identify appropriate current state tool for data comparison. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Platform
17 | Improve validation of HHAs in the HPD referral pool | HPD | (HPD) Compare daily file of HPD HHA update information against current HHA HPD pool. Remove HHAs from the pool based on data validations. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Platform
17 | Improve validation of HHAs in the HPD referral pool | HPD | (HPD) Confirm approach for removal of HHAs from the pool based on cross-referenced information with HPD legal and DHS. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Process
17 | Improve validation of HHAs in the HPD referral pool | DHS/HPD | (DHS/HPD) Evaluation and establishment of a notification and reasonable accommodations process for removal of HHAs from the pool to ensure that shelter residents are not being removed due to incorrect or outdated data. | Medium-term | High | HPD HPS uses available HHA information to house shelter residents. However, due to the gap in time between when an HHA is submitted and the first match, which can be months, the HHA information becomes stale due to changed circumstances (e.g., household identified other housing opportunity, household moved out of shelter). To better support HPS in getting access to needed information, this BPI involves DHS and HRA establishing a daily data feed to HPD to allow HPD to create an automated daily match of HPD HHA information with the following data sources to identify shelter residents that may no longer need housing support or whose Cash Assistance, income, or household composition information changes. To support the current state, HPD can use the unique identifiers across matches, SSN, DHS Case Number. In the future state, this should be considered for scope within the future state enterprise system (BPI #22). | Process
18 | Establish an automated process for updating the HHA | HPD | (HPD) Identify which information will require regular updates or validation, such as income, household size, neighborhood preferences, etc. | Medium-term | High | Provide an interim solution for improving the accuracy of the HHA information used for the shelter resident/unit match pending HPD’s long term technology objectives for the homeless set-aside placement process. Currently there is no automated mechanism for DHS to update the information in the HHA even though a household circumstance may change (e.g., change in location preference, household size, etc.) while the HHA remains pending. An HHA could be submitted and pending a match for months. | Process
18 | Establish an automated process for updating the HHA | DHS | (DHS) Work with the HOME developer, to build automated requests for updates to the HHAs in HOME. This will include alerts or flag for when a change has been made in the HHA. | Medium-term | High | Provide an interim solution for improving the accuracy of the HHA information used for the shelter resident/unit match pending HPD’s long term technology objectives for the homeless set-aside placement process. Currently there is no automated mechanism for DHS to update the information in the HHA even though a household circumstance may change (e.g., change in location preference, household size, etc.) while the HHA remains pending. An HHA could be submitted and pending a match for months. | Platform
18 | Establish an automated process for updating the HHA | DHS | (DHS) Work with the HOME developer to create monthly reminders for shelter providers to validate HHA data elements or make changes as needed. | Medium-term | High | Provide an interim solution for improving the accuracy of the HHA information used for the shelter resident/unit match pending HPD’s long term technology objectives for the homeless set-aside placement process. Currently there is no automated mechanism for DHS to update the information in the HHA even though a household circumstance may change (e.g., change in location preference, household size, etc.) while the HHA remains pending. An HHA could be submitted and pending a match for months. | Platform
18 | Establish an automated process for updating the HHA | HPD | (HPD) Use a low code or no code solution to flag in the daily data feed where HHA update were made, such as through an alert or visual flag. Use the CARES ID and SSN as a unique identifier. Generate an excel file that reflects recently updated HHAs and update the HHA pool in the MS Access database as needed. | Medium-term | High | Provide an interim solution for improving the accuracy of the HHA information used for the shelter resident/unit match pending HPD’s long term technology objectives for the homeless set-aside placement process. Currently there is no automated mechanism for DHS to update the information in the HHA even though a household circumstance may change (e.g., change in location preference, household size, etc.) while the HHA remains pending. An HHA could be submitted and pending a match for months. | Platform
19 | Optimize shelter resident/unit matching | DHS/Shelter | (DHS/Shelter providers) Leverage the tool to inform the shelter resident on how their selections and preferences may affect their possibility for a match. Additionally, update any outreach material or resident-facing material to include information about how personal preferences/constraints may affect a match to a unit. | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Platform
19 | Optimize shelter resident/unit matching | HPD | (HPD) Confirm matching logic and prioritization according to information elicited from the HHA and key details related to the HPD housing stock. | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Platform
19 | Optimize shelter resident/unit matching | HPD | (HPD) Develop a configurable "Matching Support" model and algorithm to optimize matching per the data elements in the HHAs, data elements of the available units, and the matching logic. Identify data elements that would be weighted by the shelter resident to generate a score that indicates the strength of the match. The matching tool will generate a match score that indicates how closely the unit aligns with the household's needs, including composition, neighborhood preferences or restrictions, accommodation needs, and other factors. | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Platform
19 | Optimize shelter resident/unit matching | HPD | (HPD) Establish policies based upon the strength of the match generated for each referral, including BPI 10: Implement a policy to limit the number of units a shelter resident can reject. | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Process
19 | Optimize shelter resident/unit matching | HPD | (HPD) Develop a feedback mechanism to obtain data on successful/unsuccessful matches and further improve the matching algorithm for continuous improvement. | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Process
19 | Optimize shelter resident/unit matching | HPD | (HPD) Conduct analysis on how HHA selections may impact matching outcomes. Share information with DHS for sharing with shelter residents | Long-term | High | Reduce the manual nature of HPD HPS’ matching process, improve accuracy of the match, and help facilitate discussions between DHS shelter providers and shelter residents on how their housing preferences and the prioritization of their housing preferences may affect their likelihood of a match with a unit in HPD HPS’ pipeline. This involves creating an easy to maintain and customizable optimization tool that automates the shelter resident/unit matching. From a DHS perspective, the tool should be used to explain to shelter residents on how their prioritization of their own preferences impacts can limit or impact access to available HPD set-aside housing. This can provide shelter residents more transparency to set expectations on move-out. | Process
20 | HPD to work with DHS on Planned Pipeline and Potential Referrals | HPD | (HPD) Develop report that includes high-level summary of aside units available (by location, size, reasonable accommodations), and units that are planned to be available. Distribute report to DHS. | Short-term | Medium | Accelerate lease-up by proactively sharing information with DHS about the pipeline of units for improved alignment with the HHA pool (i.e., that the pool of HHA reflects households with needs and preferences that align to HPD’s pipeline supply). HPD should conduct regular reviews of existing and projected affordable housing stock and review this information with DHS HRPU. It is important to note that pipeline monitoring applies primarily to known set-aside units. Information on volunteered units should be communicated as soon as they are known. To support this, HPD should provide DHS an estimated number of referrals they target to receive monthly. This information should be derived by looking at planned construction planned for HPD that is likely to become available as well as leverage trends to-date. This information from HPD include information such as potential housing compositions and neighborhoods. | Process
20 | HPD to work with DHS on Planned Pipeline and Potential Referrals | HPD | (HPD) Establish regular meetings with DHS HPRU to review unit pipeline and highlight currently available units that do not have referrals. | Short-term | Medium | Accelerate lease-up by proactively sharing information with DHS about the pipeline of units for improved alignment with the HHA pool (i.e., that the pool of HHA reflects households with needs and preferences that align to HPD’s pipeline supply). HPD should conduct regular reviews of existing and projected affordable housing stock and review this information with DHS HRPU. It is important to note that pipeline monitoring applies primarily to known set-aside units. Information on volunteered units should be communicated as soon as they are known. To support this, HPD should provide DHS an estimated number of referrals they target to receive monthly. This information should be derived by looking at planned construction planned for HPD that is likely to become available as well as leverage trends to-date. This information from HPD include information such as potential housing compositions and neighborhoods. | Process
20 | HPD to work with DHS on Planned Pipeline and Potential Referrals | HPD/DHS | (HPD/DHS) Discuss process and program updates and areas of improvement (e.g., not enough HHAs, incomplete or inaccurate HHAs) | Short-term | Medium | Accelerate lease-up by proactively sharing information with DHS about the pipeline of units for improved alignment with the HHA pool (i.e., that the pool of HHA reflects households with needs and preferences that align to HPD’s pipeline supply). HPD should conduct regular reviews of existing and projected affordable housing stock and review this information with DHS HRPU. It is important to note that pipeline monitoring applies primarily to known set-aside units. Information on volunteered units should be communicated as soon as they are known. To support this, HPD should provide DHS an estimated number of referrals they target to receive monthly. This information should be derived by looking at planned construction planned for HPD that is likely to become available as well as leverage trends to-date. This information from HPD include information such as potential housing compositions and neighborhoods. | Process
20 | HPD to work with DHS on Planned Pipeline and Potential Referrals | DHS | (DHS) Incorporate recurring office hours or Q&A sessions for shelter level staff to provide further training and education on the homeless set-aside placement process. | Short-term | Medium | Accelerate lease-up by proactively sharing information with DHS about the pipeline of units for improved alignment with the HHA pool (i.e., that the pool of HHA reflects households with needs and preferences that align to HPD’s pipeline supply). HPD should conduct regular reviews of existing and projected affordable housing stock and review this information with DHS HRPU. It is important to note that pipeline monitoring applies primarily to known set-aside units. Information on volunteered units should be communicated as soon as they are known. To support this, HPD should provide DHS an estimated number of referrals they target to receive monthly. This information should be derived by looking at planned construction planned for HPD that is likely to become available as well as leverage trends to-date. This information from HPD include information such as potential housing compositions and neighborhoods. | Process
21 | Create live dashboard to support performance management | HDC/HPD | (HDC/HPD) Work with Inter-Agency Task Force to identify key data elements to track in the dashboard. ­- The referral statuses developed by the OMB Policy and Operations Research Task Force that have been used for this evaluation so far should serve as the starting point. | Medium-term | High | Leverage the work of the OMB Policy and Operations Research Task Force started and create an automated, easy to configure and maintain reporting solution to monitor the performance of the homeless set-aside placement process and provide transparency to the status of units and households. This will help HPD track performance against targets, identify process stalls, and evaluate the effectiveness of the BPIs proposed by this assessment—as well as areas for continuous process improvement. Recommended data sources include the HOME daily data feed, HPS MS Access Database, manual data entry abstracts used by the HPS unit today, and CurRENT. | Platform
21 | Create live dashboard to support performance management | HDC/HPD | (HDC/HPD) Business users to identify key business needs for the dashboard (e.g., ability to generate reports, access permissions, access for multiple City agency users). | Medium-term | High | Leverage the work of the OMB Policy and Operations Research Task Force started and create an automated, easy to configure and maintain reporting solution to monitor the performance of the homeless set-aside placement process and provide transparency to the status of units and households. This will help HPD track performance against targets, identify process stalls, and evaluate the effectiveness of the BPIs proposed by this assessment—as well as areas for continuous process improvement. Recommended data sources include the HOME daily data feed, HPS MS Access Database, manual data entry abstracts used by the HPS unit today, and CurRENT. | Platform
21 | Create live dashboard to support performance management | (HDC/HPD/HRA) | (HDC/HPD/HRA) Assess for data sharing with HOME and CurRENT and data sharing agreements that need to be established. Since HPD already has access to CurRENT and receives data from HOME new agreements may not be needed. | Medium-term | High | Leverage the work of the OMB Policy and Operations Research Task Force started and create an automated, easy to configure and maintain reporting solution to monitor the performance of the homeless set-aside placement process and provide transparency to the status of units and households. This will help HPD track performance against targets, identify process stalls, and evaluate the effectiveness of the BPIs proposed by this assessment—as well as areas for continuous process improvement. Recommended data sources include the HOME daily data feed, HPS MS Access Database, manual data entry abstracts used by the HPS unit today, and CurRENT. | Platform
21 | Create live dashboard to support performance management | HDC/HPD | (HDC/HPD) Work with technical resources (external or internal City resources) to identify reporting solution for the dashboard creation. | Medium-term | High | Leverage the work of the OMB Policy and Operations Research Task Force started and create an automated, easy to configure and maintain reporting solution to monitor the performance of the homeless set-aside placement process and provide transparency to the status of units and households. This will help HPD track performance against targets, identify process stalls, and evaluate the effectiveness of the BPIs proposed by this assessment—as well as areas for continuous process improvement. Recommended data sources include the HOME daily data feed, HPS MS Access Database, manual data entry abstracts used by the HPS unit today, and CurRENT. | Platform
21 | Create live dashboard to support performance management | (HDC/HPD/HRA/DHS) | (Inter-Agency Task Force) Conduct regular performance management discussions using dashboard and reports generated. Identify areas of improvement in operations. | Medium-term | High | Leverage the work of the OMB Policy and Operations Research Task Force started and create an automated, easy to configure and maintain reporting solution to monitor the performance of the homeless set-aside placement process and provide transparency to the status of units and households. This will help HPD track performance against targets, identify process stalls, and evaluate the effectiveness of the BPIs proposed by this assessment—as well as areas for continuous process improvement. Recommended data sources include the HOME daily data feed, HPS MS Access Database, manual data entry abstracts used by the HPS unit today, and CurRENT. | Process
22 | Implement enterprise-wide HPD placement system | (HDC/HPD/HRA/DHS) | (HPD/DHS/HRA/HDC) Begin to implement process changes to achieve the desired future state homeless set-aside placement process (key items noted in BPI 1, 2, 6, 7, 9, 16, 17, 19, 21, 31) | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Process
22 | Implement enterprise-wide HPD placement system | HPD | (HPD) Review unit data elements and identify any updates needed to correspond to additional data elements being collected on the HHA related to borough preferences and constraints. | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Platform
22 | Implement enterprise-wide HPD placement system | HPD | (HPD) Identify confirm different modules and persona who would use the future state system. Develop use cases for personas (identified in the report) | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Platform
22 | Implement enterprise-wide HPD placement system | HPD | (HPD) Develop technical requirements and integrations needed for the future state case system leveraging the system diagram found in Appendix F: Homeless set-aside placement future state systems diagram. Consider not only current integrations but desired integrations that would improve the process. | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Platform
22 | Implement enterprise-wide HPD placement system | HPD | (HPD) Identify solution easy to configure for the homeless set-aside placement process and case management needs. | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Platform
22 | Implement enterprise-wide HPD placement system | HPD | (HPD) Identify technical resources to support configuration of the solution. | Long-term | High | Implement an enterprise-wide HPD placement system to modernize and automate the homeless set-aside placement process. This solution would help provide end-to-end support to the homeless set-aside process, transforming the process from one that is manual with multiple handoffs and siloed information to one that is automated, streamlined, and consolidates access to information based on user roles | Platform
23 | Increase staffing within Centralized Budget Team unit with “New Needs” request | HRA | (HRA) Identify resource needs for the CBT team to meet target times and reduce backlogs in rebudgeting. | Short-term | Low | For a shelter resident to be eligibility for CityFHEPS they need to have a CA case, either Active or in SI status. CA determination for shelter residents is handled by HRA CBT and these activities can take several days to weeks to complete. CBT currently does not have sufficient resources to meet the needed workload, with only 3 full-time employees. To address this, HRA should align CBT resourcing with current cash assistance caseloads to reduce impact to lease up time. HRA will need to submit a “new needs” request for addition CBT staffing as part of the November plan. | People
23 | Increase staffing within Centralized Budget Team unit with “New Needs” request | HRA | (HRA) Prepare new needs request for the November plan. Submit to OMB. | Short-term | Low | For a shelter resident to be eligibility for CityFHEPS they need to have a CA case, either Active or in SI status. CA determination for shelter residents is handled by HRA CBT and these activities can take several days to weeks to complete. CBT currently does not have sufficient resources to meet the needed workload, with only 3 full-time employees. To address this, HRA should align CBT resourcing with current cash assistance caseloads to reduce impact to lease up time. HRA will need to submit a “new needs” request for addition CBT staffing as part of the November plan. | Process
24 | Confirm alignment on keeping SI cases open past 30 days | HRA | (HRA) Confirm with HRA legal team on process to obtain OTDA approval to keep SI cases (used for housing vouchers) “active” for a longer timeframe and to allow for additional time to deliberate an SI case, if needed. | Short-term | Medium | Reduce disruptions to the homeless set-aside placement process and subsidy processing that are caused by State rules for CA. HRA needs to seek a waiver or approval from OTDA that would allow the SI case to be open for over 30 days without any State audit findings against HRA. The homeless set-aside placement process can possibly extend beyond 30 days, especially when a shelter resident is matched to a LIHTC unit, and the 30-day limitation on the SI case creates a difficult timeline to meet and resolving SI case closures can prolong the lease up. This BPI will allow DHS the opportunity to continue to work with the client without running the risk that the SI case will need to re-open, it will reduce CBT backlog for having to reopen the case and it will mitigate HRA concerns on not sufficiently meeting audit needs. | Process
25 | DHS should initiate CA case changes when a shelter resident accepts a unit | DHS | (DHS) Implement policy and procedural changes to initiate CA case changes when a shelter resident accepts a unit. Provide training and support to DHS staff on changes. | Medium-term | Low | Reduce delays during the CityFHEPS subsidy processing step (currently 44 days) that are associated with corrections to the CA case or opening the CA case which is a time-consuming process. DHS should initiate CA case changes the moment a shelter resident accepts a unit to remove this from the critical path for lease-up. | Process
26 | Consolidate all DHS CA case management activities under HRPU | DHS | (DHS) Confirm HRPU capacity to take on additional workload. | Medium-term | Medium | HRPU should consolidate activities for CA to eliminate handoffs among DHS business units. To do this, HRPU own all CA case revisions for all household types. | People
26 | Consolidate all DHS CA case management activities under HRPU | DHS | (DHS) Mention to other stakeholders on change in assignment. | Medium-term | Medium | HRPU should consolidate activities for CA to eliminate handoffs among DHS business units. To do this, HRPU own all CA case revisions for all household types. | Process
27 | DHS to approve CityFHEPS for cases that are in Active or Single Issuance status that do not have income | DHS | (DHS) Identify needed resources to support HRPU approval of CityFHEPS voucher. | Long-term | Low | DSS can reduce hand-offs in the CityFHEPS voucher process by having HRPU make the final approval of CityFHEPS cases instead of HRA, specifically those who have Active or SI cases without income. By having HRPU take on this eligibility approval function, approval steps between HRPU and HRA will be eliminated. HRPU currently has the same level of information as HRA to the needed systems to execute needed tasks by validate a client has no income, specifically TALX, WMS and CurRENT. Additionally, single adults and adult family cases are often the most complex, and often result in an SI status. | People
27 | DHS to approve CityFHEPS for cases that are in Active or Single Issuance status that do not have income | DHS | (DHS) Develop transition plan to account for hiring and training of additional resources. | Long-term | Low | DSS can reduce hand-offs in the CityFHEPS voucher process by having HRPU make the final approval of CityFHEPS cases instead of HRA, specifically those who have Active or SI cases without income. By having HRPU take on this eligibility approval function, approval steps between HRPU and HRA will be eliminated. HRPU currently has the same level of information as HRA to the needed systems to execute needed tasks by validate a client has no income, specifically TALX, WMS and CurRENT. Additionally, single adults and adult family cases are often the most complex, and often result in an SI status. | People
28 | HRA to waive 30-day CityFHEPS income requirement for Active Cash Assistance and Single Issuance cases with income | HRA | (HRA) Consider procedure change to CityFHEPS eligibility, specifically remove the need to validate income for CA clients with an open case in Active or SI status. To start this, engage HRA legal and NYC Law Department as appropriate to conduct review of legal of legal landscape and consider interaction with OTDA requirements for other types of public assistance (SNAP, CA, etc.). | Long-term | Medium | The current CityFHEPS rule requires employment verification at the time of the CityFHEPS application, irrespective of the employment income available on the CA case. This creates delays in processing by duplicative client asks as well as additional workload for CBT, an understaffed unit. This BPI recommends that for household with an active CA case, the previously collected and verified employment income can serve as an alternative to requesting proof of employment income again at the time of CityFHEPS packet submission. | Process
28 | HRA to waive 30-day CityFHEPS income requirement for Active Cash Assistance and Single Issuance cases with income | HRA | (HRA) Follow agency rulemaking process to amend the current CityFHEPS rules with the determined language changes. | Long-term | Medium | The current CityFHEPS rule requires employment verification at the time of the CityFHEPS application, irrespective of the employment income available on the CA case. This creates delays in processing by duplicative client asks as well as additional workload for CBT, an understaffed unit. This BPI recommends that for household with an active CA case, the previously collected and verified employment income can serve as an alternative to requesting proof of employment income again at the time of CityFHEPS packet submission. | Process
28 | HRA to waive 30-day CityFHEPS income requirement for Active Cash Assistance and Single Issuance cases with income | HRA | (HRA) Update agency policies and procedures to implement CityFHEPS rule amendment that will no longer require the re-checking of income for households with active CA cases. | Long-term | Medium | The current CityFHEPS rule requires employment verification at the time of the CityFHEPS application, irrespective of the employment income available on the CA case. This creates delays in processing by duplicative client asks as well as additional workload for CBT, an understaffed unit. This BPI recommends that for household with an active CA case, the previously collected and verified employment income can serve as an alternative to requesting proof of employment income again at the time of CityFHEPS packet submission. | Process
28 | HRA to waive 30-day CityFHEPS income requirement for Active Cash Assistance and Single Issuance cases with income | HRA/DHS | (HRA/DHS) Update and develop training and tools for shelter providers and shelter residents to understand policy changes and reinforce their responsibility to report changes in income as required at any time, within 10 days of a significant change in income. | Long-term | Medium | The current CityFHEPS rule requires employment verification at the time of the CityFHEPS application, irrespective of the employment income available on the CA case. This creates delays in processing by duplicative client asks as well as additional workload for CBT, an understaffed unit. This BPI recommends that for household with an active CA case, the previously collected and verified employment income can serve as an alternative to requesting proof of employment income again at the time of CityFHEPS packet submission. | Process
29 | DSS to leverage NYS integrated eligibility system modernization to eliminate system workarounds | HRA/DHS | (DSS) Document requirements for future IES solution | Long-term | High | DSS is a primary stakeholder in OTDA’s replacement of their legacy WMS platform, known as the IES project. Given the additional scope and flexibility IES will offer across programs, this can offer improvement to various DSS current-state capabilities, including the management of CA caseloads. Given DSS will be an active participant in IES requirements and design sessions, they should identify requirements that will support the HPD set-aside process as it relates to CA eligibility. | Platform
30 | Pursue approval for phone interviews for active CA cases | HRA | (HRA) Engage HRA Legal and the NYC Law Department, as needed, to assess details of requested waiver for in-person interviews. | Long-term | Medium | Pursue approval to conduct “add-an-adult case interviews” via phone instead of in person. Currently a key part of the backlog for CA cases are household with a CA case, where a new household member is reported. When this occurs, a case change needs to be reported to FIA CBT, and an interview must occur with the new household. | Process
30 | Pursue approval for phone interviews for active CA cases | HRA | (HRA) assess FIA capacity to manage Employment Plan interview through phone interviews. | Long-term | Medium | Pursue approval to conduct “add-an-adult case interviews” via phone instead of in person. Currently a key part of the backlog for CA cases are household with a CA case, where a new household member is reported. When this occurs, a case change needs to be reported to FIA CBT, and an interview must occur with the new household. | People
31 | Improve marketing agent engagement through quarterly or semi-annual meetings | HPD | (HPD) Identify engagement meeting attendees and schedule marketing agent quarterly meeting. | Short-term | Low | Improve marketing agent performance and compliance with the homeless set-aside placement process by helping HPD shift their engagement methods from announcements and compliance to an ongoing focus on building effective partnerships. Enhance marketing agent engagement through the establishing of quarterly meetings with agents like how DHS leadership meets with shelter providers monthly. | Process
31 | Improve marketing agent engagement through quarterly or semi-annual meetings | HPD | (HPD) Establish agendas and elicit feedback from marketing agents on agenda topics. | Short-term | Low | Improve marketing agent performance and compliance with the homeless set-aside placement process by helping HPD shift their engagement methods from announcements and compliance to an ongoing focus on building effective partnerships. Enhance marketing agent engagement through the establishing of quarterly meetings with agents like how DHS leadership meets with shelter providers monthly. | Process
31 | Improve marketing agent engagement through quarterly or semi-annual meetings | HPD | (HPD) Generate reports on marketing agent performance leveraging OMB Policy and Operations Research Task Force data as a starting point. Share metrics with marketing agents related to lease-up and details related to demand for housing and potential future demands. | Short-term | Low | Improve marketing agent performance and compliance with the homeless set-aside placement process by helping HPD shift their engagement methods from announcements and compliance to an ongoing focus on building effective partnerships. Enhance marketing agent engagement through the establishing of quarterly meetings with agents like how DHS leadership meets with shelter providers monthly. | Process
31 | Improve marketing agent engagement through quarterly or semi-annual meetings | HPD | (HPD) Assess cadence to determine the appropriate frequency for most beneficial meetings with marketing agents. | Short-term | Low | Improve marketing agent performance and compliance with the homeless set-aside placement process by helping HPD shift their engagement methods from announcements and compliance to an ongoing focus on building effective partnerships. Enhance marketing agent engagement through the establishing of quarterly meetings with agents like how DHS leadership meets with shelter providers monthly. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | (HPD/HDC/DHS) | (HPD/HDC/DHS) Develop clear understanding of shelter resident journey to understand their process, barriers, and experience in the homeless set-aside placement program, documenting program expectations, responsibilities, and policies applicable to the resident. | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | DHS/HPD | (DHS/HPD) Develop a communication plan to engage shelter residents through a targeted rollout of the outreach and information material, including informing shelter residents of how they can access these materials, integrating into the shelter intake and case management process, and overall information-sharing plan for the city (i.e., 3-1-1). | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | DHS/HPD | (DHS/HPD) Draft communication material with human-centered design principles. Communications material to address program expectations and shelter resident rights and responsibilities for a variety of learning styles and needs (key notes within report of communication material inputs) | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | DHS/HPD | (DHS/HPD) Incorporate any shelter resident-specific policies, including those identified in BPI 5: Remove the LIHTC eligibility appointment from the LIHTC eligibility determination process, BPI 9: Document and enforce a LIHTC document submission timeline for shelter residents, and BPI 12: Implement a process step and timeframe for obtaining resident acceptance/rejection of unit. | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | HPD | (HPD) Draft a plain-language checklist listing various examples of documents that will or may be requested during this process, specifically for LIHTCH. Clarify what will be required and what may be requested if applicable. | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process
32 | Develop shelter resident homeless set-aside placement process toolkit | DHS/HPD | (DHS/HPD) Develop a plan to train shelter providers on how and when to communicate these outreach materials to shelter residents and how to contact HPD with questions and concerns. Develop a retraining plan to account for staff turnover/attrition and program changes. | Short-term | Medium | The homeless set-aside placement program is currently the second largest program for people living in NYC DHS shelter to exit into long-term housing yet there is no information publicly available to shelter residents providing an end- to-end view of the process and what is expected of their participation. The goal of this BPI is to support shelter resident experience and ability to meet program requirements as efficiently as possible by developing an easily available online toolkit (with process overview, guidance, policies, FAQs, key points of contact, etc.). The toolkit should be developed by DHS in collaboration with HPD and HRA. The toolkit could be expanded to educate shelter residents on all the different types of rental assistance and housing support programs available and help shelter residents make informed choices on participating in these programs and which one may be best for the resident and their family. | Process